## Sheet1
Group Member |  | Major Task
Harpreet Kaur | Jupyter Notebook
| Subtask | Date Started | Data Complete
| Data cleaning | 2020-02-21 | 2020-02-22
| Visualization | 2020-03-09 | 2020-03-10
| Correaltion | 2020-03-09 | 2020-03-10
Group Member |  | Major Task
Arvind Sharma | Report Writing
| Subtask | Date Started | Data Complete
| Data Loading, Data Overview | 2020-02-20 | 2020-02-21
| Introduction | 2020-03-11 | 2020-03-12
| Literature Review | 2020-03-11 | 2020-03-12
Group Member |  | Major Task
Jasleen | Jupyter Notebook
| Subtask | Date Started | Data Complete
| Data set search | 2020-02-10 | 2020-02-15
| Add test Data | 2020-03-10 | 2020-03-10
| Feature selection | 2020-03-11 | 2020-03-12
| Decision Tree Model Building | 2020-03-11
Mortgage Prediction Project timeline